## Sheet1
Task Manager / Dev | Task Description | Initial Estimate | Amount Remaining After…
|  |  | Day 1 (Monday 2) | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 (10th) | Day 10 (11th) | Day 11 (12th) | Day 12 (Friday 13)
Jacob | Implement NPC | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Kate | Implement Merchant Logic | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0
Jacob | Refactor to support NPC | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 2 | 2 | 0 | 0 | 0
Jacob | Add NPC to World | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0
Jacob | Load NPC | 3 | 3 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Jacob | NPC Movement | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0
Colby | Implement Items | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Colby | Refactor to support Items | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
Kate | Add Items to World | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 2 | 1 | 1 | 0 | 0
Kate | Implement Item/NPC interactions | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 1 | 0 | 0
Colby | Load Items | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Jacob | Random Map Gen | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0
| Estimate Totals | 29 | 29 | 25 | 21 | 21 | 21 | 19 | 19 | 19.5 | 15.5 | 9.5 | 0 | 0
Task Manager / Dev | Task Description | Actual Time | Date of Work
Kate | Checking For bug(testing game logic) and Refactoring | 6 | Thursday 12th
Jacob | View Binding and Bug Fixes | 2 | Thursday 12th
Jacob | Adding NPC to World and adding some movement | 4 | Thursday 12th
Kate | Implement Merchant Trading with UI | 2 | Wednesday 11th
Kate | Implement Merchant Trading with UI | 4 | Tuesday 10th
Jacob | Assisting kate with NPC and Item interaction | 2 | Tuesday 10th
Colby | Pick up Item and Refactor Drop Items | 2 | Tuesday 10th
Colby | Implment Items (testing for full coverage) | 1.5 | Monday 9th
Colby | Refactor Items (testing for full coverage) | 1.5 | Monday 9th
Kate | Refactor NPC | 1 | Monday 9th
Kate | Implement NPC and Item interaction | 3.5 | Monday 9th
Jacob | Refactor NPC | 1 | Sunday 8th
Jacob | Add NPC to world | 1 | Sunday 8th
Jacob | Implment NPC | 5 | Saturday 7th
Jacob | Load NPC | 1 | Saturday 7th
Colby | Refactored Items | 2 | Saturday 7th
Colby | Implmented Items | 4 | Wednesday 4th
Colby | Load Items (.txt file creation) | 2 | Tuesday 3rd
Jacob | Load NPC (.txt file creation) | 2 | Tuesday 3rd
| Actual Time Totals | 47.5