## Sheet1
Task Manager / Dev | Task Description | Initial Estimate | Amount Remaining After…
|  |  | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15
| Implement NPC | 2
| Refactor to support NPC | 2
| Add NPC to World | 0.5
| Load NPC | 3
| NPC Movement | 4
| Implement Items | 2
| Refactor to support Items | 2
| Add Items to World | 0.5
| Implement Item/NPC interactions | 5
| Load Items | 3
| Map Gen (Location) | 3
| Map Gen (NPC) | 3
| Map Gen (Item) | 3
| Estimate Totals | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Manager / Dev | Task Description | Initial Estimate
| Estimate Totals | 0