## Sheet1
Task Manager / Dev | Task Description | Initial Estimate | Amount Remaining After…
|  |  | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15
Jacob | Implement NPC | 2
Jacob | Refactor to support NPC | 2
Kate | Add NPC to World | 0.5
??? | Load NPC | 3
??? | NPC Movement | 4
Colby | Implement Items | 2
Colby | Refactor to support Items | 2
Kate | Add Items to World | 0.5
Kate | Implement Item/NPC interactions | 5
??? | Load Items | 3
??? | Map Gen (Location) | 3
??? | Map Gen (NPC) | 3
??? | Map Gen (Item) | 3
| Estimate Totals | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task Manager / Dev | Task Description | Actual Time
| Actual Time Totals | 0